FAKE CONTRACT FOR FIBER OPTIC CONNECTION

Between:
KPN B.V., located in The Hague, Netherlands, hereinafter referred to as KPN
and
VvE “Residentie De Linde,” located in Utrecht, Netherlands, hereinafter referred to as the Client or VvE
Date: November 5, 2025
Contract Number: KPN-RES-2025-041
KPN Contact Person: Gerard den Oever

- Purpose and Background
This contract aims to deliver and install a fiber optic infrastructure in the building "Residentie De Linde," consisting of 60 apartments, including the connection to the meter cabinet of each residence.
After the infrastructure is completed, residents can individually subscribe to KPN for internet, television, and telephony.
The VvE acts as the collective client for the installation and connection of the building and is responsible for access to common areas and coordination with residents.

- Scope of Services
2.1 Delivery by KPN
KPN will supply and install:
• Fiber Optic Connection to the Building (FTTB): including the main distributor in the technical room.
• In-house Distribution (FTTH): installation of a fiber optic connection from the main distributor to the meter cabinet of each residence.
• Active Equipment (ONTs): one Optical Network Terminal per residence, excluding end-user equipment (router/modem).
• Project Management: one point of contact for planning, access, communication with residents, and delivery reports.
• Delivery and Certification: signal strength and transmission quality measurements per connection.
2.2 Not Included
• Individual subscriptions (to be directly arranged by residents with KPN).
• In-house cabling after the meter cabinet.
• Civil works on private land outside the building (unless explicitly agreed).
• Costs for damage repairs outside KPN's responsibility.

- Obligations of the VvE
The VvE is responsible for:
• Providing access to technical rooms, stairwells, and common areas at agreed times.
• Communicating with residents regarding the schedule and installation dates.
• Designating a contact person (chairperson or administrator) for technical coordination.
• Availability of building plans or installation diagrams, if available.
• Facilitating a power supply (230V) near the main distributor.

- Schedule and Execution
• Start of site survey: within 4 weeks after signing.
• Installation phase: within 8 weeks after approval of the site survey and release of building plans.
• Testing phase: up to 2 weeks.
• Delivery & Handover: within 3 months from the start of work, depending on access and weather conditions.
KPN will perform the work as much as possible during office hours (08:00–17:00), unless otherwise agreed.

- Cost Structure and Payment Terms
All amounts are in euros, excluding VAT.
5.1 One-time Project Costs
| Description | Quantity | Rate per Unit | Total |
|-------------|----------|---------------|-------|
| Building connection (FTTB) including main distributor | 1 | €8,000 | €8,000 |
| In-house distribution (FTTH) to residences | 60 | €250 | €15,000 |
| Project management & delivery | 1 | €2,000 | €2,000 |
| Total one-time | | | €25,000 |

Payment:
• 40% upon confirmation of order
• 40% at the start of installation
• 20% after delivery and approval by the VvE
Optional: Residents will receive an individual discount of €75 on the connection fee when signing up for a KPN subscription within 3 months after delivery.

- Service Level Agreement (SLA)
6.1 Maintenance and Faults
• Preventive maintenance: twice per year during office hours.
• Incident response (for infrastructure, not individual subscriptions):
o Severity 1 (complete building offline): response within 2 hours, solution within 8 hours.
o Severity 2 (partial connection issue): response within 4 hours, solution within 24 hours.
o Severity 3 (non-critical issues): response within 1 business day, solution within 5 business days.
6.2 Availability
• Fault reports via KPN Business Servicedesk: 24x7 available.
• The VvE will receive a monthly status report on incidents and maintenance.
6.3 Warranty
The fiber optic installation is guaranteed for 5 years after delivery, provided that maintenance is performed through KPN.

- Safety, Privacy, and Ownership
• KPN complies with the Telecommunications Act and GDPR.
• The physical infrastructure (fibers, distribution points, and ONTs) remains the property of KPN.
• The VvE does not obtain ownership of fiber optic materials but does obtain the right to use them for residents who subscribe individually.
• Resident data will only be processed within the individual customer relationship with KPN.

- Term and Termination
• This contract is effective from the date of signing and is valid for 3 months after delivery, unless a maintenance contract is concluded.
• In case of cancellation before the start of installation, KPN may charge for costs already incurred (survey, planning, preparations), with a minimum of €2,000.

- Liability
• KPN is liable for direct damage due to negligence, up to a maximum of the contract invoice amount.
• KPN is not liable for consequential damages (e.g., loss of profit or income).
• Any damage claims must be reported in writing within 30 days of discovery.

- Transfer and Contact
KPN Project Leader:
Name: _______________________
Phone: _______________________
Email: _______________________

VvE Contact Person:
Name: _______________________
Position: ____________________
Phone: _______________________
Email: _______________________

- Signatures
The parties declare to agree to the terms as outlined above.

For KPN B.V.
Name: _______________________
Position: ____________________
Signature: _________________
Date: _______________________

For VvE Residentie De Linde
Name: _______________________
Position: ____________________
Signature: _________________
Date: _______________________