FAKE CONTRACT FOR INTERNAL TELEPHONE AND NETWORK INFRASTRUCTURE

Between:
KPN B.V., located in The Hague, Netherlands, hereinafter referred to as KPN
and
Stichting Voortgezet Onderwijs De Horizon, located in Tilburg, Netherlands, hereinafter referred to as the Client or School
Date: November 5, 2025
Contract Number: KPN-EDU-NET-2025-018
KPN Contact Person: Jasmijn van Echt

- Purpose and Background
This contract describes the delivery, installation, and maintenance of an internal communication system for Stichting Voortgezet Onderwijs De Horizon.
The system includes a modern VoIP telephony solution, a secure wireless network (WiFi 6), and a wired LAN network with central management.
The goal is to improve internal communication between teachers, administration, and management, and to ensure reliable network connectivity for classroom and office environments.

- Scope of Services
2.1 Services and Components Provided by KPN
KPN will supply and implement the following components:
• VoIP Telephony Platform:
o Central phone system (cloud-based, KPN Business Hosted Voice).
o 60 VoIP devices (Yealink T54W) for employees.
o Softphone licenses (Teams integration) for 20 users.
o Queues and call groups (administration, reception, scheduling office).
o Call forwarding to mobile via KPN Één.
• Network and Infrastructure:
o Complete LAN overhaul (Cat6 switching, PoE, VLAN segmentation).
o WiFi 6 access points (Aruba Instant On) — 35 units for coverage in classrooms and corridors.
o Network controller with cloud management and access control.
o Firewall and content filtering (Fortigate 60F).
• Management and Monitoring:
o 24x7 network monitoring, automatic firmware updates.
o Access to KPN Network Dashboard for real-time status and incident alerts.
o Monthly reports on availability and performance.
• Training and Handover:
o 1-day training for IT administrator and 2 key users.
o Documentation and manual for internal management.

- Obligations of the School
• Provide technical rooms, meter cabinets, and server rooms during installation.
• Designate an IT contact person for coordination with KPN.
• Timely approval of network diagrams and connection points.
• Ensure power supply and UPS in server room.
• Provide designated data input points per room (if available).

- Implementation Schedule
| Phase | Activity | Timeline |
|-------|----------|----------|
| 1 | Confirm site survey & design | Week 1–2 |
| 2 | Installation of cabling & equipment | Week 3–6 |
| 3 | VoIP & network management configuration | Week 7 |
| 4 | Testing phase & training | Week 8 |
| 5 | Handover & transfer | Week 9 |
Total duration: approximately 9 weeks after signing, depending on availability and access.

- Pricing and Payment Terms
All amounts in euros, excluding VAT.
5.1 One-time Costs (Implementation)
| Description | Quantity | Rate per Unit | Total |
|-------------|----------|---------------|-------|
| VoIP system & device installation | 60 | €180 | €10,800 |
| Network installation (switching, cabling, WiFi) | - | - | €18,000 |
| Firewall + configuration | 1 | €2,000 | €2,000 |
| Training & handover | 1 | €1,200 | €1,200 |
| Total one-time | | | €32,000 |

5.2 Monthly Costs (Management & Licenses)

| Description | Quantity | Rate | Total |
| --- | --- | --- | --- |
| Hosted Voice licenses | 60 | €8 | €480 |
| Softphone licenses | 20 | €4 | €80 |
| Network management & monitoring | - | €350 | €350 |
| Education Plus support package | - | €200 | €200 |
| Total per month |  |  | €1,110 |

5.3 Payment Terms
• 40% upon confirmation of order
• 40% upon delivery of hardware
• 20% after successful testing phase
• Monthly billing of management costs in advance; payment within 30 days

- Service Level Agreement (SLA)
6.1 Availability
• VoIP platform: 99.95% uptime (monthly average)
• WiFi/LAN: 99.7% uptime during office hours
• Maintenance windows: maximum 6 hours/month, announced in advance
6.2 Response and Resolution Times
| Incident Category | Response Time | Resolution Time |
|-------------------|---------------|-----------------|
| Severity 1 – complete network or telephony outage | 30 minutes | 4 hours |
| Severity 2 – partial outage or reduced functionality | 2 hours | 24 hours |
| Severity 3 – non-critical issues | 1 business day | 5 business days |
6.3 Service Credits
In case of SLA breaches, the school will receive a service credit of 5% of the monthly fee for every 0.1% below the SLA threshold, up to a maximum of 50%.

- Security and Privacy
• KPN complies with GDPR and NEN 7510 (healthcare/education standards).
• All data connections are encrypted (TLS 1.3, WPA3).
• Authentication via RADIUS and SSO integration available.
• Usage logs are retained for 6 months, solely for incident investigation.

- Ownership and Management
• Equipment remains the property of KPN during the contract period.
• The school obtains the right to use the equipment for the duration of the agreement.
• Upon contract termination, the school can acquire the equipment at book value.
• Software licenses are non-transferable.

- Term and Termination
• Initial term: 36 months from delivery date.
• Notice period: 60 days before end of term.
• Early termination only by mutual written agreement.
• After the term, automatic renewal per year unless canceled in writing.

- Liability
• KPN's liability is limited to a maximum of 12 months of management fees per calendar year.
• KPN is not liable for indirect damages (e.g., class cancellations or lost income).
• Outages caused by external providers or local power failure are not covered.

- Contact Persons
For KPN B.V.
Name: ________________________
Position: Project Manager Education ICT
Email: ________________________
Phone: ________________________

For Stichting Voortgezet Onderwijs De Horizon
Name: ________________________
Position: ICT Coordinator
Email: ________________________
Phone: ________________________

- Signatures
The parties declare that they have read, understood, and agree to the terms of this contract.

For KPN B.V.
Name: ________________________
Signature: ____________________
Date: _________________________

For Stichting Voortgezet Onderwijs De Horizon
Name: ________________________
Signature: ____________________
Date: _________________________